## Detail
GMO RUNSYSTEM CORPORATION |  |  |  | Total | Done | Open | Not Open | Start Over | Finish Over |  |  | Update: | 2014-06-13 | [70 empty] | Date： 2014/06/13
KidISO Project Schedule |  |  |  | 8 | 0 | 0 | 8 | 0 | 0 |  |  | Creator: | HaiPT | [70 empty] | GMO RUNSYSTEM CORPORATION
Summary Information
[5 empty] | 2014-06-16 | 2014-07-04 |  |  | 34 |  | 0 |  |  | 2014 | 6 | [18 empty] | 7 | [30 empty] | 8 | [18 empty] | Note
No | Screen No | Screen Name | Task/Function | Person | Plan |  | Actual |  | Cost Plan |  | Cost Actual |  | Progress | time axis 2014-06-12 to 2014-08-19
[5 empty] | Start | Finish | Start | Finish | Hours | Days | Hours | Days | time axis 2014-06-12 to 2014-08-19
1 |  |  | Create enviroment | HaiPT | 2014-06-13 | 2014-06-16 |  |  | 8 | 1 |  |  |  | ▲ | 2014-06-13: 4; 2014-06-16: 4
2 |  |  | Login page | HaiPT | 2014-06-17 | 2014-06-18 |  |  | 12 | 1.5 |  |  |  | ◇ | 2014-06-17: 8; 2014-06-18: 4
3 |  |  | System admin page | BangHH | 2014-06-16 | 2014-06-18 |  |  | 24 | 3 |  |  |  | ◇ | 2014-06-16: 8; 2014-06-17: 8; 2014-06-18: 8
4 |  |  | Sub admin page | BangHH | 2014-06-19 | 2014-06-23 |  |  | 20 | 2.5 |  |  |  | ◇ | 2014-06-19: 8; 2014-06-20: 8; 2014-06-23: 4
5 |  |  | School admin page | BangHH | 2014-06-23 | 2014-06-25 |  |  | 20 | 2.5 |  |  |  | ◇ | 2014-06-23: 4; 2014-06-24: 8; 2014-06-25: 8
6 |  |  | Page profile& edit profile | BangHH | 2014-06-26 | 2014-06-27 |  |  | 16 | 2 |  |  |  | ◇ | 2014-06-26: 8; 2014-06-27: 8
7 |  |  | Teacher page | HaiPT | 2014-06-18 | 2014-06-27 |  |  | 60 | 7.5 |  |  |  | ◇ | 2014-06-18: 4; 2014-06-19: 8; 2014-06-20: 8; 2014-06-23: 8; 2014-06-24: 8; 2014-06-25: 8; 2014-06-26: 8; 2014-06-27: 8
8 |  |  | Pupil page | TueTC | 2014-06-16 | 2014-06-27 |  |  | 80 | 10 |  |  |  | ◇ | 2014-06-16: 8; 2014-06-17: 8; 2014-06-18: 8; 2014-06-19: 8; 2014-06-20: 8; 2014-06-23: 8; 2014-06-24: 8; 2014-06-25: 8; 2014-06-26: 8; 2014-06-27: 8
9 |  |  | Test | All | 2014-06-30 | 2014-07-04 |  |  | 40 | 5 |  |  |  | ◇ | 2014-06-30: 8; 2014-07-01: 8; 2014-07-02: 8; 2014-07-03: 8; 2014-07-04: 8
10
11
12
Note on Q9: Input Start date of schedule

## Setting
Holidays
No. | Day | Note
1 | 2013-09-02 | 独立記念日
2 | 2014-01-01 | 年始 | 8 | Plan | 8 | Actual | 30 | Current Date
3 | 2014-01-29 | ベトナムお正月
4 | 2014-01-30 | ベトナムお正月 |  | 0-99% |  | 100% |  | Saturday
5 | 2014-01-31 | ベトナムお正月
6 | 2014-02-01 | ベトナムお正月 | ◇ | Not yet | △ | Open |  | Sunday, Holiday
7 | 2014-02-02 | ベトナムお正月
8 | 2014-02-03 | ベトナムお正月 | ★ | finish over | ○ | Done
9 | 2014-02-04 | ベトナムお正月
10 |  |  | ▲ | start over
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## use_guide
○ |  | cong viec da hoan thanh 100%
★ |  | cong viec da bi over deadline
△ |  | Cong viec dang thuc hien (dung nhu plan)
◇ |  | cong viec chua start
Chu y: | Nhung cell khong duoc phep input (chuong trinh se bao loi khi co tinh change gia tri)
thi khong can phai input ma chuong trinh tu dong tinh toan va fill ket qua ra
Step2: nhap ngay start, cac ngay con lai se tu dong thay doi theo
ex) 2012/10/1
Ngay hien tai
Step4: nhap so gio du dinh vao o ben tren (nhap luc tao plan)
khi xoa hoac add them 1 task thi bat buoc phai copy 2 rows roi delete/ insert cung 1 luc
Step1: Thay doi ten project tuong ung
Step3: Nhap cac thong tin lien quan den task:
ScreenNo, Screen name, function name, PG name
Step5: nhap thong tin ngay change va nguoi change
Step6: nhap ngay nghi le trong nam vao sheet Setting
khi set ngay thi la 2012/10/08 thi tren sheet schedule mau cua cot tuong ung voi ngay do se change thanh mau giong ngay chu nhat
Step7: nhap so gio da thuc hien that vao o ben duoi (nhap sau khi ket thuc 1 ngay lam viec)
Step8: nhap so phan tram cong viec da hoan thanh (tu PG uoc luong va input)
cost du dinh va cost that su (tu dong tinh toan)